## Mahesh
Date | Tasks | Status | Challenges | Query | Response | Bug
2021-08-02
2021-08-03
2021-08-04
2021-08-05
2021-08-06
2021-08-09
2021-08-10
2021-08-11
2021-08-12
2021-08-13
2021-08-16
2021-08-17
2021-08-18
2021-08-19
2021-08-20
2021-08-23
2021-08-24
2021-08-25
2021-08-26
2021-08-27
2021-08-30
2021-08-31

## Bhavik
Date | Tasks | Status | Challenges | Query | Response | Bug
2021-08-02
2021-08-03
2021-08-04
2021-08-05
2021-08-06
2021-08-09 | Defined Architecture to run test via apkand GUI format. Defined config.json format and made sample config.json file Started understanding code for mocking | Completed Completed In progress
2021-08-10 | Worked to access picocom command directly via adb | On Hold | Tried multiple way to check this functionality using different commands and scripts but did not getsuccess | If we will not able to achieve this via host machine, how to trigger MCU shell commands?
| Tested all utilities with new build | Completed
| -> Updated tasks for hrm and ott issue -> Reminder to Andrew on workplace regarding MCU flash steps | Completed
2021-08-11
2021-08-12
2021-08-13
2021-08-16
2021-08-17
2021-08-18
2021-08-19
2021-08-20
2021-08-23
2021-08-24
2021-08-25
2021-08-26
2021-08-27
2021-08-30
2021-08-31

## Meet
Date | Tasks | Status | Challenges | Query | Response | Bug
2021-08-02
2021-08-03
2021-08-04
2021-08-05
2021-08-06
2021-08-09
2021-08-10
2021-08-11
2021-08-12
2021-08-13
2021-08-16
2021-08-17
2021-08-18
2021-08-19
2021-08-20
2021-08-23
2021-08-24
2021-08-25
2021-08-26
2021-08-27
2021-08-30
2021-08-31

## Kaushendra
Date | Tasks | Status | Challenges | Query | Response | Bug
2021-08-02 | Find Sensor Specific start/stop APIs from HAL Sensor start/stop API (integration) into the Test utility code Compiling and Debugging error | In progress | Calling Protected Methods of Base Class Api
| Stress test binary build for ALT sensor and run test | Completed
| Validate memory utilization over time. | Completed
2021-08-03 | - Compile new utilities for each sensor to perform stress testing - As part of stress testing, Made shell script to run utility in background and log test start and test end time in a file. | Completed
| - run the device under stress test for 4 sensor (raised Task Ticket for Ott and Hrm sensor issue) | Completed |  |  |  | OTT Sensor Not working HRM Sensor not working
| 1.Test different sensor with MCU reset. 2.Stress test binary build for ALT sensor(with timeout of every 2 secs) and run test 3.Sensor start/stop API (integration) | Completed Completed In progress | Calling Protected Methods of Base Class Api
2021-08-04 | compile MCU_Sensor.cpp start/stop API Methods in Alttest.cpp | on hold | Getting Service binding issue | Discussed with FRL , implementing Apk so to get acces to app api’s exposed to Sensor Manager | FRL Agreed to switch on APK based testing approach
| testing the utility | Completed | Utilities run with some exception
2021-08-05 | working on Developing a Sensor Test application for Pressure Sensor in andriod studio | In progress
| Apk will generate the Result.csv | In progress
2021-08-06 | working on Developing a Sensor Test application for Pressure Sensor in andriod studio | Completed | trying to integrate a json config reading and parsing mechanism
| Apk will generate the Result.csv | Completed
| apk will run in suspended mode-code integration | Completed
| running the apk through adb shell commands | Completed
2021-08-09 | Defined Architecture to run test via apk and GUI format. Defined config.json format and made sample config.json file Writing json parser code in andriod studio | Completed Completed In progress
2021-08-10 | Developing a Sensor Test application for Pressure Sensor trying to integrate a json config reading and parsing mechanism andriod studio Integrated Text-box GUI for Idle and Running stage of apk | Completed
2021-08-11 | Developing a Sensor Test application for Heart Rate Sensor trying to integrate a json config reading and parsing mechanism andriod studio Integrated Text-box GUI for Idle and Running stage of apk | Completed | Added permissions to get the heart rate sensor <uses-permission android:name="android.permission.BODY_SENSORS"/>
2021-08-30
2021-08-31