## Sheet1
Sr.Name | Sensor Name | Implementation Status | Received Output Log | How to invoke (query) | Notes from Facebook
1 | IMU sensor | Not completed | No | Not getting any reference from sensor HAL | Are you subscribing to the IMU sensor ID? I think we have an ID for IMU but it shouldn't be there. Instead of IMU you should use ACC and GYR (accelerometer and gyroscope) which you already seem to have implemented. So you don't need to test the IMU individually
2 | Heart Rate Sensor | Done | Yes | Sensor starts automatically
3 | pressure | Done | Yes | Need to start "SensorLogger.apk" from GUI
4 | Magnetometer | Pending | No | Not getting any reference from sensor HAL | Is this in reference to the Hall-effect Sensor (HES)? That sensor will only trigger when the device is inserted or removed from the cradle. But by design it is supposed to send you the current reading when you subscribe. If you are not seeing this value change when removing the device from cradle then this is abug
5 | Ambient Light Sensor | Done | No | Its only part of SOC | Yes, we currently don't expose this sensor on the MCU side of the framework, you don't need to worry about testing this currently.
6 | Gyro | Done | Yes | Sensor starts automatically
7 | Accelerometer | Done | Yes | Sensor starts automatically
8 | PPG Sensor | Pending | No | Getting error in prebuilt ppg_generated.h file (unused variable) | Can you share more details/error logs with this issue?
9 | Pedometer virtual sensor | Done | No | Not getting any data and we are not sure how to trigger activation | Currently the only way to get step data is to shake the device. Using the other shell commands as an example you could add a shell command to set the pedometer count manually for testing.
10 | Significant motion virtual sensor | Done | No | Not getting any data and we are not sure how to trigger activation | This only triggers when the device is under a lot of motion and may currently have a bug. Someone at facebook was looking into a bug with this recently, will have to follow up with you.
11 | Calories virtual sensor | Done | Yes | After starting "workout" from GUI, it is publishing data only once
12 | Respiratory Rate Virtual Sensor | Not completed | No | Not getting any reference from sensor HAL | This sensor is deprecated, you do not need to test it
13 | On Wrist Detection Virtual Sensor | Done | No | Not getting any data and we are not sure how to trigger activation | This was only added recently, you might need to pull the latest code for it to work. It required the device to have something placed close to the proximity sensor within the HRM sensor. You can also use the shell comamnd "owd_set <in_cradle> <on_wrist>" where the params are 0 = false, 1 = true
14 | Wrist Tilt Virtual Sensor | Done | No | Not getting any data and we are not sure how to trigger activation | You can use the shell command "tilt_set" to invoke this event.
15 | Temperature Debug Virtual Sensor | Done | Yes | Need to start "SensorLogger.apk" from GUI
16 | RR Interval virtual sensor | Done | No | Not getting any data and we are not sure how to trigger activation | This will be hard to test natrually, you can add a shell command to call this method to provide fake values: https://github.com/facebookexternal/Zephyr/blob/master/merlot/src/sensor/sfw_rri.c#L28
17 | OTT (LifeQ debugging) virtual sensor | Done | Yes | Sensor starts automatically
18 | Position dead reckoning virtual sensor | Pending | No |  | This is difficult to test as it requires motion. You could again add a shell command to invoke the message sending in sfw_pdr.c by providing fake pdr_update_t values: https://github.com/facebookexternal/Zephyr/blob/master/merlot/src/sensor/sfw_pdr.c#L123
19 | HRV RMSSD virtual sensor | Done | No | Not getting any data and we are not sure how to trigger activation | Entry point to mock data from the shell for this would be here: https://github.com/facebookexternal/Zephyr/blob/master/merlot/src/sensor/sfw_hrv.c#L96
20 | Activity Detection virtual sensor | Done | No | Not getting any data and we are not sure how to trigger activation | Activity detection requires motion as well. You can fake data with a shell command calling into sfw_motion.c