## Intro
Template Version: 2.3
Minutes Of Meeting
FRL_Wearable_Device
Confidentiality Notice Copyright (c) 2019 eInfochips. - All rights reserved This document is authored by eInfochips and is eInfochips intellectual property, including the copyrights in all countries in the world. This document is provided under a license to use only with all other rights, including ownership rights, being retained by eInfochips. This file may not be distributed, copied, or reproduced in any manner, electronic or otherwise, without the express written consent of eInfochips.

## Document Details (hidden)
Document History
Version | Author |  | Reviewer |  | Approver
| Name | Date (DD-MMM-YYYY) | Name | Date (DD-MMM-YYYY) | Name | Date (DD-MMM-YYYY)
Draft 0.1 | SEPG | 2010-01-12 | SEPG Head | 2010-01-12 | Council | 2010-01-12
Draft 0.2 | SEPG | 2010-01-13 | SEPG Head | 2010-01-13 | Council | 2010-01-14
Baseline 1.0 | SEPG | 2010-01-15 | SEPG Head | 2010-01-15 | Council | 2010-01-15
2 | SEPG | 2010-01-18 | SEPG Head | 2010-01-18 | Council | 2010-01-18
Baseline 2.1 | Bhairavi Shah | 2014-05-27 | Bijal Chudgar | 2014-05-28 | Bijal Chudgar | 2014-05-29
Baseline 2.2 | Akshay Panchal | 2017-01-09 | Mansi Naik | 2017-03-22 | Bijal Chudgar | 2017-04-28
Baseline 2.3 | Vipendra Tripathi | 2019-02-17 | Praveen P | 2019-02-21 | Bijal Chudgar | 2019-02-27
Version | Description Of Changes
Draft 0.1 | Created initial draft version (Mantis ID : 0000001)
Draft 0.2 | Updated as per Mantis ID : 0000001
Baseline 1.0 | Baseline
2 | Mantis ID: 1342(Mantis ID: 1342)
Baseline 2.1 | File Naming Conventions standardized across QMS artifacts (it covers all artifacts that are global, specific to S/W, H/W, ASIC or Aerospace).
Baseline 2.2 | - The 'Document Details' Tab remains intact, but to be released in a hidden mode. Hence, hiding the 'Document Details' Tab. - Removed the note indicating that the document history needs to be udpated by the project team (as project team will not have to update history section under documents of the Type "Forms")
Baseline 2.3 | Updated Company Logo.
Definition/Acronym/Abbreviation
Definition/Acronym/Abbreviation |  | Description
References
S.No | Document | Version | Remarks

## MOM
Minutes Of Meeting"
Date (Rows can be merged) | Agenda (example: Weekly Status Call, Milestone Review) | Actual Duration | Attendees | Points Discussed | Actionable Items | Responsible Person | Target Date of Completion | Actual Date of Completion | Action Item Status | Remarks
2021-06-03 | First Call with FRL Team | 1.0 Hr | : Surender Thaneer, Ravi Dua, Mahesh Patel, Bhavik Panchal, Meetkumar Bariya, Kaushendra Sah, Prajose John | FRL expectation of this project was shared by Raghu Documents shared by FRL github login to be created and access provided to EIC team Test framework expectation was discussed MCU source code availablity over github | EIC to share names of team members needing access to github FRL to upload source code over github for MCU FRL to share all documents related to MCU hw / sw architecture, Bluelink Protocol | EIC FRL | 2021-06-04 | 2021-06-04 | Done
2021-06-09 | Weekly Call with FRL Team | 1.0 Hr | : Raghu Mallampati, Alfred Tan, Surender Thaneer, Ravi Dua, Bhavin Patel, Mahesh Patel, Bhavik Panchal, Meetkumar Bariya, Kaushendra Sah, Prajose John | EIC proposed 3 approach to test the MCU firmware: 1. Use Zephyr internal test framework (Z-test) to develop the test cases 2. Use python test framework on the SoC host which will interface with bluebox server to trigger test cases via the adb shell on MCU 3. Develop Testapp in the android application framework which will use the android services to communicate using the bluebox interface to MCU Firmware Expectation of Facebook from developing test framework viz MCU Test Harness - APIs testing, MVP scenarios, Different configurations tests, audio test, display test, MCU health system enhancement, MCU Logging Query from EIC was discussed-Third party software for emulator, packages for emulator, NXP SDK, HOST PC operating system, VS code build setup Access to Android source code | FRL proposed to use option 2 as final approach to developing test framework. EIC to work on POC to check how python tests can access directly the bluebox interface FRL will provide document to set expectation out of test framework, document for APIs, document to tests to be developed for monitoring MCU FRL will post the Android source code for EIC FRL will help resolve the emulator third party dependency and point to the Zephyr root file system | EIC FRL | 2021-06-11 |  | Done
2021-06-10 | Weekly Call with FRL Team | 1.0 Hr | : Raghu Mallampati, Surender Thaneer, Ravi Dua, Mahesh Patel, Bhavik Panchal, Meetkumar Bariya, Kaushendra Sah, Prajose John | EIC mentioned about all the work done till date - Developed Pytest framework and test scripts to call C APIs to emulate the python script calling C APIs in Bluebox interface - Discussed on the MCU build successful -Discussed on the gerrit access ( not able to) -Discussed on the board shipment & availability -Discussed on the bug filing process | :-EIC to share screenshot of gerrit landing page -EIC to share range of IP address to give access to Tasks -Facebook to share Setup guide for Boards -EIC will commit code to gerrit, Facebook will help to build and upload it to dropbox. EIC to download from dropbox -EIC to demonstrate one test case implementation based on option-2. Pytest framework will sit on external PC and use the adb bridge to run testscripts | EIC FRL | 2021-06-23 |  | In Progress