## Intro
Weekly Status Report <WSR>
Wearable Devices FRL
Confidentiality Notice Copyright (c) 2021 eInfochips. - All rights reserved This document is authored by eInfochips and is eInfochips intellectual property, including the copyrights in all countries in the world. This document is provided under a license to use only with all other rights, including ownership rights, being retained by eInfochips. This file may not be distributed, copied, or reproduced in any manner, electronic or otherwise, without the express written consent of eInfochips. Template Version: 1.3

## Document Details
Document History
Version | Author |  | Reviewer |  | Approver
| Name | Date (DD-MMM-YYYY) | Name | Date (DD-MMM-YYYY) | Name | Date (DD-MMM-YYYY) | *Note: <The details written into document history should be deleted and updated according to project requirements.>
0.1 | Prajose John | 2021-06-07
Version | Description of Change
Definition/Acronym/Abbreviation
Definition/Acronym/Abbreviation |  | Description
References
# | Document | Version | Remarks

## Guideline
Sr. # | General Instructions
1 | Always take a copy of the WSR <Week No> into new tab to update the status of a particular week and hide the past week status report. And keep the WSR <Week no> tab intact, this is to ensure that you have a blank template available for creating upcoming week's WSR.
2 | Update the current week's WSR tab updated with Week number
3 | Add more items to any of the tables by copying an existing row and inserting in the next line (this is to ensure that the drop down options and the validations are intact for a new entry).
Sr. # | Field Name | Guideline
1 | Date | Enter the reporting week's starting date in cell B1. in the <DD-MMM-YY> OR <DD-MM-YY> format.
2 | Work Week | The corresponding Work Week Number, will be auto-calculated once the reporting week's start date is entered.
3 | Audience | Update the names / details of target audience who would be receiving the WSR
Sr. # | Field Name | Ongoing activities (Last Week's Goals and Milestones)
1 | Status | List the task in 3 sub group a) Tasks Completed; b) Task Not Completed and c) Unplanned task Completed. Describe the activity / Task name (from Task Tracker or PMS tool)
2 | Description | Mentioned detailed description for the activity / Task name.
Sr. # | Field Name | Current /Next Week's Goals and Milestones
1 | Task Planned | Describe the activity / Task name (from Task Tracker or PMS tool)
2 | Activity Name / description | Describe the activity / Task name (from Task Tracker or PMS tool) which is planned for, in the upcoming reporting week
Sr. # | Field Name | Schedule Slips and Recovery Action
1 | Schedule Slips | Describe / provide details where Schedule slippage is observed
2 | Recovery Action | Mention Action plan to cover up delay for smooth execution of primary tasks / activities and achieve the committed timelines.
Sr. # | Field Name | Open Issue / Risk / Dependencies / Action
1 | Description | Describe / provide reference to any Open Issue / Risk / Dependencies / Action items (internal / external) which may have impact on existing activity / task in progress.
2 | Owner | Specify the name of stake holder or a group of stakeholders, who is responsible to take suitable actions against the identified Open Issue / Risk / Dependencies / Action.
3 | Expected closure date | Mention the date <DD-MMM-YY> by which the reported Open Issue / Risk / Dependencies / Action item needs to be acted upon & closed.
4 | Status | Choose the current status of the specified action item, from amongst: Open / Closed
Sr. # | Field Name | Deliverables by Einfochips
1 | Deliverables | Describe the Deliverables / Milestones
2 | Date of Delivery (Scheduled) | Mention the expected Delivery (Scheduled) date in <DD-MMM-YY> format
3 | Date of Delivery (Actual) | Mention the actual Delivery (Schedule) date in <DD-MMM-YY> format
4 | Output | Describe / provide details on the output delivered

## WSR Week 3
Date | 2021-06-17 |  | Work Week |  | Work Week 25 |  | Guideline | 1899-12-31
Audience |  |  | Raghu Mallampati, Surender Thaneer, Ravi Dua, Bhavin Patel, Prajose John, Mahesh Patel, Bhavik Panchal, Meetkumar Baria, Kaushendra Sah
Ongoing activities (Last Week's Goals and Milestones)
# | Status |  | Description
Tasks Completed
1 | Completed |  | Android Repo Download
2 | Completed |  | Develop Pytest code on Host PC
3 | Completed |  | Develop Test code, Cross-Compile in Android, Develop C-library, Develop APIs
4 | Completed |  | Execute Code from Pytest -->adbshell-->Android API-->testcode-->response back to adbshell / file
5
Task Not Completed
1 | In Progress |  | Android Code walkthrough
2 | In Progress |  | Study Bluebox API
3 | In Progress |  | Interface with Bluebox API
4 | In Progress |  | Develop Test cases (listing of tests)
5
Unplanned task Completed
1 | Completed |  | Install VM Server
2 | Completed |  | Dropbox installation / Setup
3
4
5
Current /Next Week's Goals and Milestones
# | Task Planned |  | Activity Name / description
1 | Android Code understanding |  | Complete framework understanding
2 | Interface with Bluebox API |  | Write test code to interface with Bluebox API, collect response and send it over adb interface using python function
3 | Listing of Testcases |  | Identification of various tests under different categories
4
5
Schedule Slips and Recovery Action
# | Schedule Slips |  | Recovery Action
1
2
3
4
5
Open Issue / Risk / Dependencies / Action
I / R / D / A | Priority 1(h) / 2(m) / 3(l) | Description / Impact | Impact High / Medium / Low | Owner | Mitigation Plan for Risks | Expected closure date
Deliverables by Einfochips
# | Deliverables |  | Date of Delivery (Scheduled) |  | Date of Delivery (Actual) | Output
1
2
3
4
5

## WSR Week 4
Date | 2021-06-24 |  | Work Week |  | Work Week 26 |  | Guideline | 1899-12-31
Audience |  |  | Surender Thaneer, Ravi Dua, Bhavin Patel, Prajose John, Mahesh Patel, Bhavik Panchal, Meetkumar Baria, Kaushendra Sah
Ongoing activities (Last Week's Goals and Milestones)
# | Status |  | Description
Tasks Completed
1 | Completed |  | Board recovery proces - QFIL - > 1. Referred NED process document provided by Facebook to flash the device 2. Used Ubuntu 18.04 Host PC (laptop) to flash the device (fastboot mode) - Board bricked 3. Used Ubuntu 18.04 Host PC(laptop) to recover the board (QFIL process) - Cannot recover 4. Used Ubuntu 16.04 Host PC (desktop) to recover the board (QFIL process) - Board recovered 2. Used Windows 10 Host PC to flash the device (fastboot mode) - Board bricked 3.
2 | Completed |  | Following dependencies are identified - API listing, gerrit, workplace, tasks
Task Not Completed
1 | In Progress |  | Android Code walkthrough - - framework understanding(completed) - Bluebox API - Bluelink Protocol - topics - pub / sub implementation
2 | In Progress |  | Using Fastboot mode to flash binary. ( Note… adb devices not able to list the device )
3 | In Progress |  | Prepare Test Plan - End-to-End testing, API testing, Interface testing
4 | In Progress |  | Validating if Laptop / Desktop / Ubuntu version is playing any role in point 4 ( board recovery process)
5 | In Progress |  | Develop one test case as part of feasibility
Unplanned task Completed
1
2
3
4
5
Current /Next Week's Goals and Milestones
# | Task Planned |  | Activity Name / description
1 | Android Code walkthrough |  | framework understanding, Bluebox API, Bluelink Protocol, topics, pub / sub implementation
2 | Using Fastboot mode to flash |  | Follow document and flash the device
3 | Test Plan document |  | Define test setup, Identify test cases related to APIs, End-to-end testing, interface testing
4 | Develop one test case as part of feasibility |  | Write test code to interface with Bluebox API, send command /collect response using the Bluelink protocol (pub/sub) and send it over adb interface using python function
Schedule Slips and Recovery Action
# | Schedule Slips |  | Recovery Action
1
2
3
4
5
Open Issue / Risk / Dependencies / Action
I / R / D / A | Priority 1(h) / 2(m) / 3(l) | Description / Impact | Impact High / Medium / Low | Owner | Mitigation Plan for Risks | Expected closure date
D | D | workplace | High | Facebook |  | 1-July, 2021
D | D | gerrit | High | Facebook |  | 1-July, 2021
D | D | tasks | High | Facebook |  | 1-July, 2021
D | D | links in documents | Medium | Facebook |  | 1-July, 2021
D | D | API lists | High | Facebook |  | 1-July, 2021
Deliverables by Einfochips
# | Deliverables |  | Date of Delivery (Scheduled) |  | Date of Delivery (Actual) | Output
1
2
3
4
5

## WSR Week 5
Date | 2021-06-30 |  | Work Week |  | Work Week 27 |  | Guideline | 1899-12-31
Audience |  |  | Ravi Dua, Bhavin Patel, Prajose John, Mahesh Patel, Bhavik Panchal, Meetkumar Baria, Kaushendra Sah
Ongoing activities (Last Week's Goals and Milestones)
# | Status |  | Description
Tasks Completed
1 | Completed |  | Using Fastboot mode we are able to flash binary and with specific cable the adb devices is able to list the device
2 | Completed |  | Validated with Windows desktop / Ubuntu desktop ( board recovery process is successful)
3 | Completed |  | Developed one test case, Cross compiled and Flashed on the board, Communicated via PC (python script) --request + response tested from SoC only (not tested with Bluebox interface to MCU)
4 | Completed |  | Identified topics and API's inside MCU code as part of uBluelink Publishing APIs
5 | Completed |  | Identified all missing source code directories which is part of vendor/oculus/software/ by checking out git branch "facebook/mos-11-eic"
6 | Completed |  | Referred Getting started guide shared by Surender(Getting-started-with-Milan-Wiki.pdf) for display settings
Task Not Completed
1 | In Progress |  | Develop test case using the Bluebox APIs (to communicate with MCU)
Unplanned task Completed
Current /Next Week's Goals and Milestones
# | Task Planned |  | Activity Name / description
1 | Android Code walkthrough |  | framework understanding, Bluebox API, Bluelink Protocol, topics, pub / sub implementation
2 | Test Plan document |  | Define test setup, Identify test cases related to APIs, End-to-end testing, interface testing
3 | Develop one test case as part of feasibility |  | Write test code to interface with Bluebox API, send command /collect response using the Bluelink protocol (pub/sub) and send it over adb interface using python function
Schedule Slips and Recovery Action
# | Schedule Slips |  | Recovery Action
1
2
3
4
5
Open Issue / Risk / Dependencies / Action
I / R / D / A | Priority 1(h) / 2(m) / 3(l) | Description / Impact | Impact High / Medium / Low | Owner | Mitigation Plan for Risks | Expected closure date
D | D | workplace (for Bhavik) | High | Facebook |  | 9-July, 2021
D | D | gerrit (for Prajose ) | High | Facebook |  | 9-July, 2021
D | D | tasks (for all) | High | Facebook |  | 9-July, 2021
D | D | API lists | High | Facebook |  | 9-July, 2021
D | D | BlueCapture Sample code expected outcome | High | Facebook |  | 9-July, 2021
D | D | End-to-End testing expected outcome | High | Facebook |  | 9-July, 2021
Deliverables by Einfochips
# | Deliverables |  | Date of Delivery (Scheduled) |  | Date of Delivery (Actual) | Output
1 | Test Plan document |  | 12th July, 2021
2
3
4
5

## WSR Week 6
Date | 2021-07-07 |  | Work Week |  | Work Week 28 |  | Guideline | 1899-12-31
Audience |  |  | Ravi Dua, Bhavin Patel, Prajose John, Mahesh Patel, Bhavik Panchal, Meetkumar Baria, Kaushendra Sah
Ongoing activities (Last Week's Goals and Milestones)
# | Status |  | Description
Tasks Completed
1 | Completed |  | Identified & captured all schemas / messages associated with the topics in MCU & SoC. This will help for test case buildup
2 | Completed |  | Dynamically generating a .html file to represent the output of the results fetched from the file pulled from the adb shell of the device
3 | Completed |  | Understand and executed one Sensor based test using Bluecapture utility via Commandrouter. EIC was not able to see the output of this command. Need help from Facebook to parse this command
Task Not Completed
1 | In Progress |  | Android AOSP code understanding to develop test case using the Bluebox APIs (to communicate with MCU)
2 | In Progress |  | Test Plan document to capture all the test objective, test execution strategy, entry criteria, exit criteria, expected output
3 | In Progress |  | Sample test case development using Bluebox APIs
Unplanned task Completed
Current /Next Week's Goals and Milestones
# | Task Planned |  | Activity Name / description
1 | Android Code walkthrough |  | Android AOSP code understanding to develop test case using the Bluebox APIs (to communicate with MCU)
2 | Test Plan document |  | Test Plan document to capture all the test objective, test execution strategy, entry criteria, exit criteria, expected output
3 | Develop one test case as part of feasibility |  | Sample test case development using Bluebox APIs
Schedule Slips and Recovery Action
# | Schedule Slips |  | Recovery Action
1
2
3
4
5
Open Issue / Risk / Dependencies / Action
I / R / D / A | Priority 1(h) / 2(m) / 3(l) | Description / Impact | Impact High / Medium / Low | Owner | Mitigation Plan for Risks | Expected closure date
D | D | workplace (for Bhavik) | High | Facebook |  | 16-July, 2021
D | D | gerrit (for Prajose, repo not accessible to Kaushendra) | High | Facebook |  | 16-July, 2021
D | D | tasks (for all), working with personal account for Prajose, Bhavik | High | Facebook |  | 16-July, 2021
D | D | API lists | High | Facebook |  | 16-July, 2021
D | D | BlueCapture Sample code expected outcome | High | Facebook |  | 16-July, 2021
D | D | Documents explaining overall Uis and sensor information | High | Facebook |  | 16-July, 2021
D | D | End-to-End testing expected outcome | High | Facebook |  | 16-July, 2021
Deliverables by Einfochips
# | Deliverables |  | Date of Delivery (Scheduled) |  | Date of Delivery (Actual) | Output
1 | Test Plan document |  | 16th July, 2021
2
3
4
5

## WSR Week 7
Date | 2021-07-14 |  | Work Week |  | Work Week 29 |  | Guideline | 1899-12-31
Audience |  |  | Ravi Dua, Bhavin Patel, Prajose John, Mahesh Patel, Bhavik Panchal, Meetkumar Baria, Kaushendra Sah
Ongoing activities (Last Week's Goals and Milestones)
# | Status |  | Description
Tasks Completed
1 | Completed |  | Android AOSP code understanding to develop test case using the Bluebox APIs (to communicate with MCU)
2 | Completed |  | Sample test case development using Bluebox APIs
3 | Completed |  | Used Python script to drive the output of the API into the log file. Pull logfile to external PC and display on HTML
Task Not Completed
1 | In Progress |  | Replicating the task of getting output from all the 20 sensors
2 | In Progress |  | Test Plan document to capture all the test objective, test execution strategy, entry criteria, exit criteria, expected output
3 | In Progress |  | Listing of other APIs to be tested
4 | In Progress |  | Work on the Audio testing
Unplanned task Completed
Current /Next Week's Goals and Milestones
# | Task Planned |  | Activity Name / description
1 | Testing with remaining sensors |  | develop test case using the Bluebox APIs to test the remaining sensors
2 | Test Plan document |  | Test Plan document to capture all the test objective, test execution strategy, entry criteria, exit criteria, expected output
3 | API Testing |  | Listing out all the APIs to be tested and plan to execute those APIs
4 | Audio Testing |  | Understand the Audio code implementation
Schedule Slips and Recovery Action
# | Schedule Slips |  | Recovery Action
1
2
3
4
5
Open Issue / Risk / Dependencies / Action
I / R / D / A | Priority 1(h) / 2(m) / 3(l) | Description / Impact | Impact High / Medium / Low | Owner | Mitigation Plan for Risks | Expected closure date
D | D | tasks for Prajose | High | Facebook |  | 26-July, 2021
D | D | API lists | High | Facebook |  | 28-July, 2021
D | D | Sensor behavior / output | High | Facebook |  | 26-July, 2021
D | D | Document explaining the utilities to test all features | High | Facebook |  | 26-July, 2021
Deliverables by Einfochips
# | Deliverables |  | Date of Delivery (Scheduled) |  | Date of Delivery (Actual) | Output
1 | Test Plan document |  | 26th July, 2021
2
3
4
5