## Sheet1
Sr. No | Sensor Name | Implementation Status | Independent Apk Development | Test Suit Apk Integration | Received Output Log | Mocking Required | Mocking Command | Mocking implemented by EIC | How to invoke (query) | Sensor_Result.csv Message Schema | Notes from Facebook | EIC Action required as per comments | EIC Feedback
1 | IMU sensor | Not completed |  |  | No | NA |  |  | Not getting any reference from sensor HAL |  | Are you subscribing to the IMU sensor ID? I think we have an ID for IMU but it shouldn't be there. Instead of IMU you should use ACC and GYR (accelerometer and gyroscope) which you already seem to have implemented. So you don't need to test the IMU individually | No need to test
2 | Heart Rate Sensor | Done | Done | Done | Yes | N |  |  | Sensor starts automatically | const msgs::sensors::Hrm* hrmMsg (int64_t)hrmMsg->timestamp_ns() hrmMsg->bpm() (SensorStatus)hrmMsg->confidence() |  |  | Not getting data in latest build. Created Bug in Tasks (T97038610)
3 | pressure | Done | Done | Done | Yes | N |  |  | Need to start "SensorLogger.apk" from GUI | const msgs::sensors::Alt* pressureMsg (int64_t)pressureMsg->timestamp_ns() (float)(pressureMsg->pressure().val1()) ((float)(pressureMsg->pressure().val2())
4 | Magnetometer | No Need to Implement |  |  | No | TBD |  |  | Not getting any reference from sensor HAL |  | Is this in reference to the Hall-effect Sensor (HES)? That sensor will only trigger when the device is inserted or removed from the cradle. But by design it is supposed to send you the current reading when you subscribe. If you are not seeing this value change when removing the device from cradle then this is abug |  | We need sensor implementation reference code in sensor HAL(Ticket raised)
5 | Ambient Light Sensor | Done |  |  | No | NA |  |  | Its only part of SOC |  | Yes, we currently don't expose this sensor on the MCU side of the framework, you don't need to worry about testing this currently. | No need to test
6 | Gyro | Done | Done | Done | Yes | N |  |  | Sensor starts automatically | const msgs::sensors::Gyr* gyrMsg (int64_t)gyrMsg->timestamp_ns() (float)(gyrMsg->gyro_x().val1()) (float)(gyrMsg->gyro_x().val2()) (float)(gyrMsg->gyro_y().val1()) (float)(gyrMsg->gyro_y().val2()) (float)(gyrMsg->gyro_z().val1()) (float)(gyrMsg->gyro_z().val2())
7 | Accelerometer | Done | Done | Done | Yes | N |  |  | Sensor starts automatically | const msgs::sensors::Acc* accMsg (int64_t)accMsg->timestamp_ns() (float)(accMsg->accel_x().val1()) (float)(accMsg->accel_x().val2()) (float)(accMsg->accel_y().val1()) (float)(accMsg->accel_y().val2()) (float)(accMsg->accel_z().val1()) (float)(accMsg->accel_z().val2())
8 | PPG Sensor | Done | Done | Done | Yes | N |  |  | Generated data and frame with Apk developement | const msgs::sensors::Ppg* ppgMsg (int64_t)ppgMsg->timestamp_ns() ir().val1 ir().val2 red().val1 red().val2 green().val1 green().val2 channel pd_range_A led_current_A int_time_s | Can you share more details/error logs with this issue? | Share logs | Log Shared on workplace
9 | Pedometer virtual sensor | Done | Done | Done | Yes | Y | pedometer set | Yes | Getting Data using mocking | const msgs::sensors::Ped* pedMsg pedMsg->steps pedMsg->timestamp_ns() | Currently the only way to get step data is to shake the device. Using the other shell commands as an example you could add a shell command to set the pedometer count manually for testing. | Implement shell command | We are able ot get sensor data for single time by sending shell command "pedometer start"
10 | Significant motion virtual sensor | Done | Done |  | Yes | Y | Sgm_set | Yes | trigger activation using Apk and getting data After Mocking(No need to shake device Now) | const msgs::sensors::Sgm* sgmMsg (int64_t)sgmMsg->timestamp_ns() | This only triggers when the device is under a lot of motion and may currently have a bug. Someone at facebook was looking into a bug with this recently, will have to follow up with you. | NA | Implemented Sensor Apk, getting data once after Shaking the device
11 | Calories virtual sensor | Done | Done | Done | Yes | N |  |  | After starting "workout" from GUI, it is publishing data only once | const msgs::sensors::Cal* calMsg (int64_t)calMsg->timestamp_ns() calMsg->kcal()
12 | Respiratory Rate Virtual Sensor | Not completed |  |  | No | NA |  |  | Not getting any reference from sensor HAL |  | This sensor is deprecated, you do not need to test it | No need to test
13 | On Wrist Detection Virtual Sensor | Done | Done | Done | Yes | Y | owd_set | Yes | Getting Data using mocking | const msgs::sensors::Owd* owdMsg (int64_t)owdMsg->timestamp_ns() (uint64_t)owdMsg->prox() (uint64_t)owdMsg->cradle() | This was only added recently, you might need to pull the latest code for it to work. It required the device to have something placed close to the proximity sensor within the HRM sensor. You can also use the shell comamnd "owd_set <in_cradle> <on_wrist>" where the params are 0 = false, 1 = true | Mocking(invocation by shell commmand) | Able to get sensor data for single time by sending shell command "owd_set"
14 | Wrist Tilt Virtual Sensor | Done | Done | Done | Yes | Y | tilt_set | Yes | Getting Data using mocking | const msgs::sensors::Tilt* tiltMsg (int64_t)tiltMsg->timestamp_ns() | You can use the shell command "tilt_set" to invoke this event. | Invocation by shell | Need to send tilt_set command
15 | Temperature Debug Virtual Sensor | Done | Done | Done | Yes | N |  |  |  | const msgs::sensors::Temp* tempMsg (int64_t)tempMsg->timestamp_ns() tempMsg->sensor (float)(tempMsg->temp().val1()) (float)(tempMsg->temp().val2()) |  |  | NA
16 | RR Interval virtual sensor | Done | Done | Done | Yes | Y | rri_set | Yes | Getting Data may be fake using Apk | const msgs::sensors::Rri* rriMsg (int64_t)rriMsg->timestamp_ns() (float)rriMsg->interval_ms() (float)rriMsg->peak_ms() | This will be hard to test natrually, you can add a shell command to call this method to provide fake values: https://github.com/facebookexternal/Zephyr/blob/master/merlot/src/sensor/sfw_rri.c#L28 | Need to add shell command | Checking into code and need to know process to flash MCU firmware.
17 | OTT (LifeQ debugging) virtual sensor | Done | Done | Done | Yes | N |  |  | Sensor starts automatically | const msgs::sensors::Ott* ottMsg (int64_t)ottMsg->timestamp_ns() (uint32_t) ottMsg->byte_count() ottMsg->data()->data() |  |  | Not getting data in latest build. Created Bug in Tasks (T97038647)
18 | Position dead reckoning virtual sensor | Done | Done | Done | Yes | Y | pdr_set | Yes | Getting Data After Mocking | const msgs::sensors::PdrEvent* pdrMsg pdrMsg->event_type() pdrMsg->flush() (int64_t)pdrMsg->timestamp_ns() pdrMsg->event() | This is difficult to test as it requires motion. You could again add a shell command to invoke the message sending in sfw_pdr.c by providing fake pdr_update_t values: https://github.com/facebookexternal/Zephyr/blob/master/merlot/src/sensor/sfw_pdr.c#L123 | Need to add shell command | Checking into code and need to know process to flash MCU firmware.
19 | HRV RMSSD virtual sensor | Done | Done | Done | Yes | Y (If rri>40, then publish automatically) | hrv_set | Yes | Getting Data After Mocking | const msgs::sensors::Hrv* hrvMsg (int64_t)hrvMsg->timestamp_ns() hrvMsg->hrv() hrvMsg->hr() (float)hrvMsg->interval() (float)hrvMsg->coverage() (float)hrvMsg->samples() (float)hrvMsg->gaps() (float)hrvMsg->method() | Entry point to mock data from the shell for this would be here: https://github.com/facebookexternal/Zephyr/blob/master/merlot/src/sensor/sfw_hrv.c#L96 | Need to add shell command | Implemented Mocking
20 | Activity Detection virtual sensor | Done | Done |  | No | Pending to Implement |  |  | Not getting any data and we are not sure how to trigger activation (May require Mocking) | const msgs::sensors::Adt* adtMsg (int64_t)adtMsg->timestamp_ns() (float)adtMsg->activity() | Activity detection requires motion as well. You can fake data with a shell command calling into sfw_motion.c | Need to add shell command | Checking into code and need to know process to flash MCU firmware.
| Build Supplied Date | Build Package Name | Build Version
| 28th June | mos_userdebug_fastboot_20210624114930_1796210.0.0_884352385503801.zip | 1796210
| 25th July | mos_userdebug_fastboot_20210723075605_1861670.0.0_336099321496602.zip | 1861670
| 31st July | mos_userdebug_fastboot_20210730112429_1878510.0.0_780461212623119.zip | 1878510
| 10th Aug, | mos_userdebug_fastboot_20210806115117_1894360.0.0_834217520561379.zip | 1894360
| 16th Aug | mos_user_fastboot_20210811230534_1811100.5030.0_395762392172356.zip | 1811100
| 23rd Aug | mos_userdebug_fastboot_20210820074725_1936060.0.0_365112858579533.zip | 1936060